## Release Packages
Cobalt Release Packages
Snapshot: verified against git 2026-07-01 ¦ Generated 2026-07-03 ¦ Source: Linear CORE-1189 umbrella + child release bundles
Major release | Minor / sub-release | Codename | Linear | Status | Linear status | ⚠ Stale? | Integration branch | dev | staging | master(=prod) | Prod deployed? | Description | Notes
Mars |  | Mars | CORE-1270 | Done | In QA | ⚠ update Linear → Done | jeremy/integration-mars | ☑ | ☑ | ☑ | No | Combined product release bundling Mercury + Saturn + Guillermo's editor/transcriber workflow + Lyra + Pluto (release-of-releases). | Merged into master (prod branch) + dev + staging. Prod deploy not yet run (no vX.Y.Z tag, deploy-prod.yml not run). Trailing gold-corpus commit 185182cf/PR #527 not yet re-promoted to all envs.
| ↳ Mercury | Mercury | CORE-1190 | Done | In QA | ⚠ update Linear → Done | jeremy/integration-product-hardening-mercury | ☑ | ☑ | ☑ | No | Admin cross-org org management + in-app multi-org (create/close/login-picker) + first-run/billing/security/RBAC hardening. | Merged into all three env branches (own PR #399 + Mars bundle); prod deploy not yet run.
| ↳ Saturn | Saturn | CORE-1191 | Done | In QA | ⚠ update Linear → Done | jeremy/integration-registration-hardening-saturn | ☑ | ☑ | ☑ | No | Registration & Subscription Lifecycle Audit remediation (CORE-1165 cluster) — student checkout/subscription, legal/compliance capture, test-coverage, webhook robustness, tenant isolation. | Merged into all three env branches via Mars bundle; prod deploy not yet run.
| ↳ Lyra | Lyra | CORE-1245 | Done | In Review | ⚠ update Linear → Done | shahruk/integration-saltier-pipeline-lyra | ☑ | ☑ | ☑ | No | Shahruk's saltier transcription pipeline (per-job modes, Parakeet ASR, graph config) + async convention-editor AI rewire. | Merged into all three env branches via Mars bundle (release PR #411 merged 2026-06-24); prod deploy not yet run.
| ↳ Pluto | Pluto | CORE-1300 | Done | In Review | ⚠ update Linear → Done | jeremy/integration-org-settings-pluto | ☑ | ☑ | ☑ | No | Organization Settings refinements — org-admin + site-admin UX fixes (nav->org-switcher, Payment-methods tab + card-on-file, Users tab + license status, Student plan, context Help panel, invite-link & license-count bug fixes). | Merged into all three env branches via Mars bundle (one nix-vendorHash straggler e5074cb9 not re-promoted from the branch tip); prod deploy not yet run.
| ↳ Earth | Earth | CORE-1550 | Done | In QA | ⚠ update Linear → Done | guillermo/integration-earth | ☑ | ☑ | ☑ | No | Combined product release bundling Guillermo's in-flight SALT/frontend fixes into one coordinated promotion (functions as a Mars sub-release). | Merged into Mars via a merged PR (integration PR #511 -> jeremy/integration-mars) and Mars is on all three env branches, so Earth is ☑☑☑.
Orion |  | Orion | CORE-1566 | In Progress | In Progress |  | release/orion | ☐ | ☐ | ☐ | No | Product release following Mars; gathers feature/fix branches that land post-Mars-cut (speaker-caseload ownership scoping, admin release-info page, PHI retention hardening, erasure/retention deletes, IDOR audit sweep, Neptune licensing epic, Magento connector, targeted bug fixes). | In progress — gathering constituents; release/orion cut post-Mars, 11 commits, not yet promoted to any env. Some constituents (CORE-1294, CORE-1298) already landed in the master base via Pluto and ride Orion automatically.
| ↳ Neptune | Neptune | CORE-1227 | In Progress | In Progress |  | feature branches (phased, on develop) | ☐ | ☐ | ☐ | No | SaaS licensing-model overhaul — phased, multi-workstream epic: user/org dual-ownership licenses, personal-org provisioning, student verification, org-context safeguards, anti-abuse controls. Committed to Orion scope (2026-06-30). | No integration branch cut yet; Phase 0 (ADRs) in review, Phase 1 (foundations) in review, Phase 2 in progress. Phases 3/4b blocked on design-committee escalations #9/#10. Neptune branches currently based on 'saturn' plan and must re-target onto release/orion.
| ↳ Bull | Bull | CORE-1628 | In Progress | In Progress |  | guillermo/integration-bull | ☐ | ☐ | ☐ | No | Sub-release of Orion: batches post-Mars SALT editor/transcriber + UI fix PRs (#529-#538) onto one integration branch, which promotes into release/orion (not directly into env branches). | All 10 constituent PRs merged into guillermo/integration-bull as of 2026-07-03 (51 commits ahead of origin/master). Bundle -> release/orion PR not yet opened; not yet in any long-lived branch.
Rust |  | Rust | CORE-1193 | Backlog | Backlog |  | jeremy/integration-performance-cache-rust (planned) | ☐ | ☐ | ☐ | No | Redis/Memorystore performance cache release — shared Redis cache for RBAC + feature-flag hot paths (permission-revocation staleness fix; latency + DB-load wins). | Backlog (infra-blocked). Component PRs (spice-rack #299, gcp-infrastructure #43) moved out of draft but integration branch not yet cut.
Transcriber Portal 1.1 |  | Transcriber Portal 1.1 | CORE-1627 | Backlog | Backlog |  | release/transcriber-portal-1.1 (not yet cut) | ☐ | ☐ | ☐ | No | SALT company/ops dashboards (General Admin / Transcription Admin / Transcriber) — productionizes the CORE-1276 frozen prototypes. Standalone WIP release, not in Orion; major-release target TBD. | Planned — WIP; 12 components (rocks/pebbles/sand: F0/F1 foundations, R1-R4, P1-P5, sand chrome) all Backlog, no PRs yet.

## Features by Release
Features by Release
Snapshot: verified against git 2026-07-01 ¦ Generated 2026-07-03 ¦ One row per constituent line item of every release manifest
Major release | Release / sub-release | Tier / Type | Feature | Description | Status | Linear status | ⚠ Stale? | dev | staging | master(=prod) | In integration branch? | Notes
Mars | ↳ Mercury | Feature | CORE-1185 — In-app multi-org (create/close/login-picker) | Create a separate org (incl. Student) from account settings (capped 25/user, one-student guard); list + close orgs (OrgAdmin only, soft-delete + cancel-at-period-end); login org picker for multi-org users. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #400; merged via Mercury -> Mars -> master.
Mars | ↳ Mercury | Refactor | CORE-1184 — Promote org-detail from dialog to first-class page | refactor(admin): /admin/orgs/[id] — pure relocation, foundation for inline management. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #395.
Mars | ↳ Mercury | Feature | CORE-1183 — Admin area: cross-org org-settings management | Manage an org's subscription licenses + professional-services wallet from the admin area without being a member, gated on global.org.manage.settings. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #396.
Mars | ↳ Mercury | Feature | CORE-1186 — Admin area: cross-org license-quantity change | PATCH /v1/admin/orgs/{id}/subscriptions/{sub_id}/quantity with 1..100 bounds + license-shrink floor (409). | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #398. Plan/tier swap deliberately deferred.
Mars | ↳ Mercury | Fix | CORE-1182 — First-run wizard silently completes on failed admin invite | verifyOrInviteAdmin now returns an error; configured invite failure -> 502 + provisioning rollback. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #394.
Mars | ↳ Mercury | Fix | CORE-1181 — Unassign license false-error on 204 No Content | saltRequest called res.json() on a 204 body; now returns undefined for 204/Content-Length:0. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #393.
Mars | ↳ Mercury | Fix | CORE-1152 — /plans page security & UX hardening | Open-redirect prevention on redirect_url, plan validation before Checkout, capability-gating, plan-selection preservation through sign-up. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #391.
Mars | ↳ Mercury | Fix | CORE-1136 — Re-invited OrgAdmin loses other org-scoped roles | syncOrgAdminRBAC now uses idempotent AddUserOrgRole instead of SetUserOrgRoles. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #390.
Mars | ↳ Saturn | Fix | CORE-1166 — P0: Student checkout anomaly recovery (paid-but-no-subscription) | Registration & Subscription Lifecycle Audit P0 finding. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | Component of CORE-1165 audit cluster.
Mars | ↳ Saturn | Fix | CORE-1167 — P0: Student subscription materialization race — missing PII verification | Registration & Subscription Lifecycle Audit P0 finding. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Feature | CORE-1168 — P0: Verify/implement student-verification backend endpoint | Registration & Subscription Lifecycle Audit P0 finding. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Feature | CORE-1169 — P0: BAA/MSA clickwrap + authority-to-bind capture in create-org wizard | Registration & Subscription Lifecycle Audit P0 finding. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Test | CORE-1170 — P0: Critical-path test-coverage backfill to 80% | Registration + subscription critical-path coverage. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Fix | CORE-1171 — P1: Webhook robustness hardening | Ordering, replay, resurrection, Clerk sync. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Test | CORE-1172 — P1: Automated BOLA (cross-org) + SQL-injection test suite |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Feature | CORE-1173 — P1: WORM enforcement for consent ledger + meaningful-assent panel |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Fix | CORE-1174 — P1: Verify & document invite token entropy |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Fix | CORE-1175 — P1: Repair agent test-execution harness | Blocked live testing during audit. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Saturn | Fix | CORE-1176 — P2: LOW-severity hardening rollup | Rate limits, input validation, secrets, dep-scan, docs. | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Lyra | Feature | CORE-1028 — Per-job converter selection via named pipeline modes | Pipeline modes (full/asr/conventions) + backend->Pub/Sub->worker wiring. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #343.
Mars | ↳ Lyra | Feature | CORE-571 — Deploy Parakeet base model to transcription pipeline | NeMo Parakeet TDT ASR converter (drop-in WhisperDecoder alternative). | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #345.
Mars | ↳ Lyra | Feature | CORE-1238 — Graph-based pipeline config (named components + DAG) | Graph/DAG pipeline config (named components + connections + ports), config v1. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #407.
Mars | ↳ Lyra | Feature | CORE-1194 — Route convention-editor AI buttons through async pub/sub pipeline | Transcribe / Apply Conventions buttons via the async pipeline. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #401.
Mars | ↳ Lyra | Feature | CORE-1029 — Gemini API ASR backend (hybrid, fused for timestamps) | Excluded from Lyra — stays a draft, not in this release. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | Explicitly excluded from Lyra bundle (PR #350 draft).
Mars | ↳ Pluto | Feature | CORE-1289 — Replace left-nav Subscription with per-org Manage | Relabel surface 'Organization settings'. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Feature | CORE-1290 — Change My Plan modal: add missing Student plan option |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Feature | CORE-1291 — Org switcher: remove Manage organization item; hide dropdown for single-org users |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Feature | CORE-1292 — Rename Professional Services tab -> Payment methods; card-on-file + billing mode | Card-on-file partially landed (hosted-setup Checkout pt 1); billing-mode selection deferred to CORE-1360. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Feature | CORE-1293 — Let a user edit their own name on org-settings page |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Fix | CORE-1294 — Shareable invite link regenerates instead of persisting |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | Merged to master via Pluto (313ef0be, merge 763a0399); already in release/orion base.
Mars | ↳ Pluto | Feature | CORE-1295 — Rename Team tab -> Users; combine members + license assignment |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Feature | CORE-1296 — Make right-side Help panel context-sensitive per active tab |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Feature | CORE-1297 — Create-a-new-org: explain what an org is + name examples |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Fix | CORE-1298 — Admin org-detail: increasing license count wrongly blocked by reduce-floor guard |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | Merged to master via Pluto (09843646, merge bb7aae21); already in release/orion base.
Mars | ↳ Pluto | Feature | CORE-1299 — Admin Create Organization modal: add missing Student plan option |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes
Mars | ↳ Pluto | Test | CORE-1366 — Edge-case coverage for billing-mode + card-on-file | Landed with CORE-1292. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | Review follow-up from CORE-1292 /finish-feature board.
Mars | ↳ Pluto | Fix | CORE-1368 — Validate Stripe return URLs / open-redirect hardening | Landed with CORE-1292. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | Security follow-up; a pre-existing open-redirect surfaced during Pluto security review.
Mars | ↳ Earth | Fix | CORE-1517 — Go to Dashboard exit on prof-services waiting screen |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #495.
Mars | ↳ Earth | Fix | CORE-1390 — NO-PHI banner: dock so it never clips content |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #497.
Mars | ↳ Earth | Fix | CORE-1441 — Cap transcription confirm dialog height so it scrolls |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #499.
Mars | ↳ Earth | Feature | CORE-1374 — Self-serve machine first-draft + reports<->editor nav + dashboard exits |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #498; final re-review PR #512 (orphaned-job guard + a11y/SQL hardening) in review.
Mars | ↳ Earth | Feature | CORE-1445 — Reports<->editor nav (bundled with CORE-1374) |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #498.
Mars | ↳ Earth | Feature | CORE-1551 — Collapsible Target Speaker combobox in new-session wizard |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #500.
Mars | ↳ Earth | Feature | CORE-1568 — Require 'I understand' ack before upload on non-prod |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #506.
Mars | ↳ Earth | Feature | CORE-1571 — Remove database selection from transcribe flow |  | Done | In QA | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #510.
Mars | ↳ Earth | Feature | CORE-1554 — SLP dashboard notification hub — tabs 1 & 2 + speakers grid | 3-tab SLP notification hub, recent-speakers grid, greeting + active-speaker count. | In Review | In Review |  | ☐ | ☐ | ☐ | No | PR #501 — changes requested + merge conflicts (DIRTY); NOT yet merged into Earth; re-targeted to release/orion per SALT-slice routing note. Verified 2026-07-01: not in any long-lived branch.
Orion | ↳ Pluto | Fix | CORE-1294 — Shareable invite link Copy in table (landed in base) |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | Merged to master via Pluto; already in release/orion base — don't re-merge. Listed here for release traceability.
Orion | ↳ Pluto | Fix | CORE-1298 — Admin license-quantity 409 mislabel (landed in base) |  | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | Merged to master via Pluto; already in release/orion base — don't re-merge.
Orion | Orion | Fix | CORE-1549 — Speaker (caseload) ownership scoping | Per-clinician visibility on SALT caseload; non-admin clinicians see only speakers they created via new speakers.view-all RBAC permission. Closes cross-tenant PII gap. | In Review | In Review |  | ☐ | ☐ | ☐ | No | PR #504, open; not yet merged into release/orion.
Orion | Orion | Feature | CORE-1283 — Admin Release Info page | New admin-area Release Info tab (behind admin.access) surfacing deployed BUILD_VERSION/BUILD_COMMIT/BUILD_DATE/NIX_OUTPUT_HASH. | In Review | In Review |  | ☐ | ☐ | ☐ | No | PR #507 (-> release/orion), open.
Orion | Orion | Feature | CORE-1501 — PHI retention window + fail-fast validation | Replace silent 365-day retention default with validating loader; prod/staging fail-fast when RETENTION_*_DAYS unset. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #492 -> mars; based off jeremy/integration-mars per 2026-06-30 decision — flows into Orion via Mars -> master -> release/orion.
Orion | Orion | Feature | CORE-1092 — Erasure/retention deletes audio + transcripts | GDPR erasure + time-based retention now delete subject's GCS session audio (per-subject erasure sweep + RetentionSweeper). | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #493 -> mars; based off jeremy/integration-mars.
Orion | Orion | Feature | CORE-1102 — Schedule the retention/de-id worker | POST /api/internal/v1/run-lifecycle (scheduler-OIDC gated) drives DB de-id/hard-delete worker + GCS audio sweep. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #508 (stacked on CORE-1092); based off jeremy/integration-mars.
Orion | Orion | Fix | CORE-1460 — IDOR DENY-audit sweep | Added structured DENY audit on transcript-write + session-comment gates + two-org cross-tenant test suite. | Done | In Review | ⚠ update Linear → Done | ☑ | ☑ | ☑ | Yes | PR #509 -> mars; based off jeremy/integration-mars.
Orion | Orion | Feature | CORE-476 — Cold-storage archive before hard-delete | Archive de-identified rows (never raw audio) to GCS WORM before hard-delete. | Deferred | Deferred |  | ☐ | ☐ | ☐ | No | Reviving PR #127; stacked on CORE-1102 (after it merges).
Orion | Orion | Feature | CORE-1389 — Magento transcription connector | Inbound push endpoints so Magento submits transcription requests and queries status, correlated by Magento-supplied ref. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | Sub-tasks CORE-1610, CORE-1611; no PR yet — scheduled/scope commitment.
Orion | Orion | Fix | CORE-1067 — Audio upload fails (HTTP 403) — transcribe job stranded | Session audio upload returns 403; transcribe job row created but blob never uploads. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | Fix pending — no PR.
Orion | Orion | Fix | CORE-1064 — First-run wizard can't bootstrap admin on a fresh instance | FK to missing Cobalt org + unmapped email-unique violation block creating any site admin. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | Fix pending — no PR. Compliance-sensitive.
Orion | Orion | Fix | CORE-763 — Infra hardening — rate-limiter leak, ctx cancel, demo-cookie Secure, XFF | Rate-limiter cleanup goroutine leak, sync ctx cancellation, demo cookie Secure, XFF spoofing. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | Fix pending — no PR. Three fixable now; XFF pending infra topology.
Orion | Orion | Fix | CORE-762 — Billing N+1 + swallowed errors in subscription lookups | N+1 CountAssignedSeats per row in ListOrgSubscriptions; swallowed errors in subscription lookups. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | Fix pending — no PR.
Orion | Orion | Fix | CORE-1632 — Transcriber portal: only shows selected org's queue (cross-org visibility blocked by RLS) | Transcriber/reviewer queue is org-scoped; internal transcribers see only one org at a time. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | Fix pending — no PR. Compliance-sensitive (cross-tenant student PII).
Orion | ↳ Neptune | Epic | CORE-1227 — Neptune — SaaS Licensing Model overhaul | Phased licensing-model overhaul (see Tab 1 Neptune row for phase detail). | In Progress | In Progress |  | ☐ | ☐ | ☐ | No | Committed to Orion scope 2026-06-30; Phase 0 in review. See CORE-1228..1236, 1644, 1261, 1353, 1462, 1463 for phase/slice detail.
Orion | ↳ Bull | Fix | CORE-1598 — Convention editor: cannot paste text into the editor | Paste (Cmd/Ctrl+V) into the ProseMirror-based convention editor was a no-op. | In Review | In Review |  | ☐ | ☐ | ☐ | No | PR #529, merged into guillermo/integration-bull; bull not yet merged into release/orion.
Orion | ↳ Bull | Fix | CORE-1597 — Transcriber portal: editor editable before transcription job completes | Transcriber editor must be read-only until ASR job completes. | In Review | In Review |  | ☐ | ☐ | ☐ | No | PR #532, merged into guillermo/integration-bull; bull not yet merged into release/orion.
Orion | ↳ Bull | Fix | CORE-1601 — Route self-serve draft completion to the editor |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Orion | ↳ Bull | Fix | CORE-1603 — Convention editor: 'View original' shows the machine draft |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Orion | ↳ Bull | Fix | CORE-1382 — Spice: cap Create Goal target-date year at 4 digits |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Orion | ↳ Bull | Fix | CORE-1600 — D/M/Y birthday picker so DOB day is selectable |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Orion | ↳ Bull | Fix | CORE-1439 — Clarify transcriber dashboard time-in-state column |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Orion | ↳ Bull | Fix | CORE-1548 — Keep autofilled inputs on-theme in dark mode |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Orion | ↳ Bull | Feature | CORE-1605 — Convention editor: detach + resume for Apply-Conventions-with-AI |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Orion | ↳ Bull | Fix | CORE-1559 — SALT caseload: show age from session stats when DOB absent |  | In Review | In Review |  | ☐ | ☐ | ☐ | No | Merged into guillermo/integration-bull (PRs #529-#538); not yet in any long-lived branch — lands only via bundle -> release/orion promotion.
Rust | Rust | Feature | CORE-823 — perf(cache): shared Redis cache for RBAC + feature-flag hot paths | GCP Memorystore (BASIC dev/staging, STANDARD_HA prod), private IP, AUTH+TLS, Secret Manager. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | spice-rack PR #299 + gcp-infrastructure PR #43 moved out of draft; integration branch not yet cut.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Foundation | CORE-1614 — F0 — Persona RBAC & role boundaries | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Foundation | CORE-1615 — F1 — Ops app shell (route group, nav, persona switcher, dashboard scaffold) | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Rock | CORE-1616 — R1 — Queue Manager (human transcriber ops) | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Rock | CORE-1617 — R2 — Timesheet + punch-clock | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Rock | CORE-1618 — R3 — Payroll | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Rock | CORE-1619 — R4 — Billing & Revenue B2B | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Pebble | CORE-1620 — P1 — Transcriber Management | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Pebble | CORE-1621 — P2 — Transcriber (Maria) portal polish | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Pebble | CORE-1622 — P3 — People / HR + performance reviews | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Pebble | CORE-1625 — P4 — Team Messaging | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Pebble | CORE-1624 — P5 — Exports (role-filtered reports) | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.
Transcriber Portal 1.1 | Transcriber Portal 1.1 | Sand | CORE-1626 — Portal chrome & polish (Accounts & Access, Audit, Settings, Help) | Component of the SALT company/ops dashboards spec (CORE-1276), decomposed rocks/pebbles/sand. | Backlog | Backlog |  | ☐ | ☐ | ☐ | No | No PR yet.

## Not in a Release
Not in a Release
Snapshot: 2026-07-01 ¦ Generated 2026-07-03 ¦ Open Core Team items (In Progress/In Review/In QA/Todo) not a constituent of any release manifest (and whose parent isn't either). Excludes Backlog and Done/Canceled.
Area | Linear | Status | Priority | Project | Assignee | Parent | Labels | Title
SALT / SaaS product | CORE-1134 | In Progress | Urgent | HIPAA/FERPA/COPPA Audit Remediation | Alok Parlikar | (none) |  | Verify frontend Vertex path fails closed + bring its config under source control
SALT / SaaS product | CORE-1318 | Todo | Urgent | SALT: UI/UX Design | Ashley Ippolito | (none) |  | UI/UX Feedback from Karen (6/3/26) & Joelle
SALT / SaaS product | CORE-1495 | In Progress | Urgent | MARS Audit Remediation (2026-06-28) | Jeremy Blair | (none) |  | [principal-engineer] Phase 1 — RBAC logic blockers (B1, SEC1, B2)
SALT / SaaS product | CORE-684 | Todo | Urgent | Levi/Ashley Product Management | Levi Wilson | (none) |  | Redesign SALT Website
SALT / SaaS product | CORE-687 | Todo | Urgent | Levi/Ashley Product Management | Levi Wilson | CORE-684 |  | Create 3 frontend mockups and gather team feedback
SALT / SaaS product | CORE-688 | Todo | Urgent | Levi/Ashley Product Management | Levi Wilson | CORE-684 |  | Connect approved mockup to backend on the cloned site
SALT / SaaS product | CORE-689 | Todo | Urgent | Levi/Ashley Product Management | Levi Wilson | CORE-684 |  | Deploy redesigned website live
SALT / SaaS product | CORE-1065 | In QA | High | QA for GTM | Guillermo Segovia | (none) | Bug, SALT | Unable to add, edit/ update, or switch organization — only one org can be created with no management options
SALT / SaaS product | CORE-1066 | In QA | High | QA for GTM | Guillermo Segovia | CORE-1065 | Bug, SALT | Onboarding org creation fails with "failed to register user" error
SALT / SaaS product | CORE-1068 | In QA | High | QA for GTM | Guillermo Segovia | CORE-1065 | SALT, Bug | Transcription editor — audio waveform stuck on "Loading waveform..." and no transcript utterances appear
SALT / SaaS product | CORE-1069 | Todo | High | QA for GTM | (unassigned) | CORE-1065 | SALT, Bug | SALT Analysis Report shows all-zero metrics — no data computed due to empty transcript
SALT / SaaS product | CORE-1070 | In QA | High | QA for GTM | (unassigned) | CORE-1065 | Bug, SALT | Speaker goal creation fails — "Create Goal" modal submits but goal is not saved
SALT / SaaS product | CORE-1071 | Todo | High | QA for GTM | (unassigned) | CORE-1065 | SALT, Bug | Subscription plan not updated after payment — shows Free Account despite subscribing to Clinician/Researcher ($49/seat)
SALT / SaaS product | CORE-1072 | In QA | High | QA for GTM | (unassigned) | CORE-1065 | SALT, Bug | Guided tour breaks after Step 8 in Demo mode — HTTP 401 "Not authorized to view this session" for demo-session-1
SALT / SaaS product | CORE-1073 | Todo | High | QA for GTM | (unassigned) | CORE-1065 | Bug, SALT | Add Speaker fails — "Failed to create speaker. Please try again." error on submission
SALT / SaaS product | CORE-1110 | In Progress | High | HIPAA/FERPA/COPPA Audit Remediation | (unassigned) | (none) |  | P1-13 — Confirm the 1 no-MFA Workspace user is a bot; MFA on all humans
SALT / SaaS product | CORE-1150 | In QA | High | SALT: Web App Core | Guillermo Segovia | (none) | SALT | Bug: Both transcribe paths dead-end in 403 license_required on POST /api/salt/jobs ("Included in plan" badge contradicts it)
SALT / SaaS product | CORE-1244 | In QA | High | SALT: Transcription Pipeline | Guillermo Segovia | (none) | SALT | Convention editor gates AI features on `transcriber.access` / Transcriber role that RBAC migration removed
SALT / SaaS product | CORE-1246 | Todo | High | Security & Identity Hardening | Jeremy Blair | (none) |  | Salt-saas Postgres tier roles via NOINHERIT-gated SET ROLE gateway
SALT / SaaS product | CORE-1276 | Todo | High | SALT: UI/UX Design | Jeremy Blair | (none) |  | SALT Company Dashboards — Frozen v2 Ready for Implementation
SALT / SaaS product | CORE-1278 | Todo | High | SALT: UI/UX Design | Jeremy Blair | CORE-1276 |  | SALT Company Dashboard — SALT Transcriber Implementation Spec
SALT / SaaS product | CORE-1279 | Todo | High | SALT: UI/UX Design | Jeremy Blair | CORE-1276 |  | SALT Company Dashboard — Transcription Admin Implementation Spec
SALT / SaaS product | CORE-1302 | In QA | High | SALT: Web App Core | Guillermo Segovia | (none) | SALT, Bug | Salt self-serve transcribe: session owner gets 403 on own job audio + segments (waveform never loads)
SALT / SaaS product | CORE-1496 | In Progress | High | MARS Audit Remediation (2026-06-28) | Jeremy Blair | (none) |  | [principal-engineer] Phase 2 — Critical guards & auth (API1, SEC2, B4)
SALT / SaaS product | CORE-1497 | In Progress | High | MARS Audit Remediation (2026-06-28) | Jeremy Blair | (none) |  | [solution-architect→principal-engineer] Phase 3 — Schema & migration safety (S1, S2, S3, S5)
SALT / SaaS product | CORE-1558 | In QA | High | QA for GTM | Guillermo Segovia | (none) | Bug, SALT | SALT: Transcription submission modal traps scroll and blocks navigation
SALT / SaaS product | CORE-1594 | In QA | High | SALT: Infrastructure and Deployment | Alok Parlikar | (none) | SALT | salt-saas dev/staging: bump Cloud SQL tier db-f1-micro → db-g1-small (DB connection exhaustion breaking backend deploys)
SALT / SaaS product | CORE-262 | In Progress | High | SALT: Web App Core | (unassigned) | (none) | SALT | Epic: SALT SaaS Direction Change — Shared Transcript Editor (Capability-Gated) + Two-Path Session Model
SALT / SaaS product | CORE-434 | Todo | High | QA for GTM | Shahruk Hossain | (none) | Bug, SALT | WebSocket Connection Error Observed on Safari During Audio Transcription
SALT / SaaS product | CORE-506 | Todo | High | SALT: Web App Core | Jeremy Blair | (none) | Feature, SALT | Add transcription → SALT convention steps between audio upload and scores
SALT / SaaS product | CORE-526 | Todo | High | SALT: Backend Architecture & API | (unassigned) | CORE-262 | Feature, SALT | P1-T1: Add `transcription_mode` to jobs/sessions schema
SALT / SaaS product | CORE-527 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T2: Session-creation UX — explicit fork "I'll transcribe" vs. "Transcribe for me"
SALT / SaaS product | CORE-528 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T3: Unit-test framework setup for `app/frontend/`
SALT / SaaS product | CORE-529 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T4: Shared editor — extract `capabilities` prop on `ConventionEditor`
SALT / SaaS product | CORE-530 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T5: Clinician session page — wire the shared editor into `/salt/sessions/[id]`
SALT / SaaS product | CORE-531 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T6: Transcriber portal — pass AI-enabled capabilities to `ConventionEditor`
SALT / SaaS product | CORE-532 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T7: Transcription-assist surface (MVP) — toolbar, tooltips, context menus, keyboard
SALT / SaaS product | CORE-533 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T8: Editor time-tracking — 30s heartbeat
SALT / SaaS product | CORE-534 | Todo | High | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P1-T9: E2E + unit-test sweep for both transcription paths
SALT / SaaS product | CORE-589 | In QA | High | SALT: Web App Core | Guillermo Segovia | CORE-830 |  | Transcriber time tracking — AFK-aware extension of editor heartbeat
SALT / SaaS product | CORE-620 | Todo | High | QA for GTM | Shahruk Hossain | (none) | Bug | .m4a Audio Upload failure
SALT / SaaS product | CORE-648 | In QA | High | SALT: Web App Core | Guillermo Segovia | CORE-829 | SALT | Transcriber editor audio player — port productivity features from Shahruk's first iteration
SALT / SaaS product | CORE-662 | In QA | High | SALT: Backend Architecture & API | (unassigned) | (none) | Bug | salt/database unit tests fail on clean Postgres because SESSION_DATABASE_URL points at cobalt_app, not postgres superuser
SALT / SaaS product | CORE-811 | In QA | High | QA for GTM | Guillermo Segovia | (none) | Bug, SALT | [Bug] SALT Reports page showing 0 for all measurements
SALT / SaaS product | CORE-812 | In QA | High | QA for GTM | Guillermo Segovia | (none) | Bug, SALT | [Bug] Failed to create new speaker
SALT / SaaS product | CORE-813 | In QA | High | QA for GTM | Guillermo Segovia | (none) | Bug, SALT | [Bug] Audio stuck in processing — transcription never completes
SALT / SaaS product | CORE-814 | In QA | High | QA for GTM | Guillermo Segovia | (none) | Bug, SALT | [Bug] Goal not being created when using Add Goal
SALT / SaaS product | CORE-815 | In QA | High | QA for GTM | Guillermo Segovia | (none) | Bug, SALT | [Bug] "Microphone permission denied" error shown even when microphone is enabled in browser
SALT / SaaS product | CORE-1074 | Todo | Medium | QA for GTM | (unassigned) | CORE-1065 | Bug, SALT | User trapped in org creation loop — "failed to register user" prevents navigation to home/dashboard and blocks sign-out
SALT / SaaS product | CORE-1086 | In QA | Medium | Security & Identity Hardening | Alok Parlikar | (none) |  | Phase 6 — Alerting &amp; detection
SALT / SaaS product | CORE-1119 | Todo | Medium | HIPAA/FERPA/COPPA Audit Remediation | Jeremy Blair | (none) |  | P2-1 — Per-schema DB credentials (or correct the docs' claim)
SALT / SaaS product | CORE-1178 | In QA | Medium | QA for GTM | Guillermo Segovia | CORE-1065 | SALT, Bug | Birthday year field allows more than 4 digits — invalid chronological age calculation
SALT / SaaS product | CORE-1202 | Todo | Medium | SALT: Transcription Pipeline | Shahruk Hossain | (none) | SALT | Migrate published S3 pipeline configs to the graph format (components + connections)
SALT / SaaS product | CORE-1214 | In Progress | Medium | SALT: UI/UX Design | Ashley Ippolito | (none) |  | Design the Caseload page — extensible tracking hub
SALT / SaaS product | CORE-1215 | Todo | Medium | SALT: UI/UX Design | Levi Wilson | (none) |  | Reports redesign — concepts for a simplified, progressive-disclosure reports experience
SALT / SaaS product | CORE-1218 | In Progress | Medium | SALT: UI/UX Design | Levi Wilson | (none) |  | Mock up the Multilingual Assessment flow + editor behavior
SALT / SaaS product | CORE-1240 | In QA | Medium | SALT: Web App Core | Guillermo Segovia | CORE-550 | Feature, SALT | Salt new-session: show an "uploading, please wait" indicator during audio upload
SALT / SaaS product | CORE-1509 | Todo | Medium | Security & Identity Hardening | Alok Parlikar | (none) |  | PAM-gate operator access to salt-saas PHI GCS buckets (no standing object read)
SALT / SaaS product | CORE-1519 | In QA | Medium | MARS Audit Remediation (2026-06-28) | Jeremy Blair | (none) |  | Remove dead prepaid-wallet code in shared/billing transcription services (post CORE-1441)
SALT / SaaS product | CORE-1542 | In Progress | Medium | SALT: UI/UX Design | Guillermo Segovia | (none) |  | RE: Dashboard with Notifications
SALT / SaaS product | CORE-521 | In QA | Medium | SALT: Web App Core | Jeremy Blair | (none) | Feature, SALT | feat(org): OrgAdmin self-serve member management (/settings/team)
SALT / SaaS product | CORE-539 | Todo | Medium | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P2-T5: Transcription-assist toolbar — full SALT code palette
SALT / SaaS product | CORE-649 | In QA | Medium | SALT: Web App Core | Guillermo Segovia | CORE-262 | SALT | Transcription editor — line numbers, cursor-position footer, and required Chronological Age gate
SALT / SaaS product | CORE-540 | Todo | Low | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P3-T1: Session Linking — side-by-side score/report comparison
SALT / SaaS product | CORE-541 | Todo | Low | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P3-T2: Print from Editor
SALT / SaaS product | CORE-542 | Todo | Low | SALT: Backend Architecture & API | (unassigned) | CORE-262 | Feature, SALT | P3-T3: `.sltdb` parser (Go) + supporting format parsers (`.slt`, `.cha`, `.sd1`)
SALT / SaaS product | CORE-543 | Todo | Low | SALT: Backend Architecture & API | (unassigned) | CORE-262 | Feature, SALT | P3-T4: Bulk import — single-file and folder upload endpoints
SALT / SaaS product | CORE-544 | Todo | Low | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P3-T5: Import UX — interactive user-mapping wizard
SALT / SaaS product | CORE-545 | Todo | Low | SALT: Web App Core | (unassigned) | CORE-262 | Feature, SALT | P3-T6: Tools menu — keyboard activation + simple comparative-database creation
SALT / SaaS product | CORE-1179 | In Progress | No priority | SALT: Metrics & Scoring Engine | Jeff Lilly | (none) | Experiment, salt-modeling | Test alternative Gemini prompts for SALT annotation modeling
SALT / SaaS product | CORE-139 | In Progress | No priority | SALT: Transcription Pipeline | arif@cobaltspeech.com | (none) | SALT, salt-modeling | Improve diarization in SALT transcripts (priority 1)
SALT / SaaS product | CORE-140 | In Progress | No priority | SALT: Transcription Pipeline | Cenk Demiroglu | (none) | SALT, salt-modeling | Prepare & Sanitize SALT Training Dataset
SALT / SaaS product | CORE-142 | In Progress | No priority | SALT: Transcription Pipeline | Cenk Demiroglu | (none) | SALT, salt-modeling | Adapt a Parakeet Model with SALT data
SALT / SaaS product | CORE-1520 | In Progress | No priority | SALT: Transcription Pipeline | stan@cobaltspeech.com | (none) | SALT, salt-modeling | Include alternate word choices in FuserDecoder output
SALT / SaaS product | CORE-1524 | In Progress | No priority | SALT: Transcription Pipeline | stan@cobaltspeech.com | (none) | salt-modeling, SALT | Trim SALT train/test data
SALT / SaaS product | CORE-1525 | In Review | No priority | SALT: Transcription Pipeline | david@cobaltspeech.com | (none) | salt-modeling, SALT | Neural C-unit segmenter: acoustic-aware (timing features from ASR timestamps)
SALT / SaaS product | CORE-1526 | In Review | No priority | SALT: Transcription Pipeline | david@cobaltspeech.com | (none) | salt-modeling, SALT | Neural EOS-mark punctuator converter (drop-in for rule-based punctuator)
SALT / SaaS product | CORE-1527 | In Review | No priority | SALT: Transcription Pipeline | david@cobaltspeech.com | (none) | salt-modeling, SALT | ErrorCodeInserterDeberta converter (DeBERTa error-code/omission tagger)
SALT / SaaS product | CORE-1528 | Todo | No priority | SALT: Transcription Pipeline | Shahruk Hossain | (none) | salt-modeling, SALT | Transcribe Train/Dev sets with Gemini for downstream component training
SALT / SaaS product | CORE-1529 | Todo | No priority | SALT: Metrics & Scoring Engine | (unassigned) | (none) | salt-modeling, SALT | Verb tagging for %Utts-with-Verbs — audit salt-scorer, add to conventions pipeline if missing
SALT / SaaS product | CORE-1530 | Todo | No priority | SALT: Infrastructure and Deployment | Shahruk Hossain | (none) | salt-modeling, SALT | Move modeling code from saltier-worker to saltier-training (git-filter export with history)
SALT / SaaS product | CORE-1531 | In Review | No priority | SALT: Infrastructure and Deployment | Shahruk Hossain | (none) | salt-modeling, SALT | Build model-bundle in flake.nix from individually-archived models
SALT / SaaS product | CORE-1532 | Todo | No priority | SALT: Infrastructure and Deployment | Shahruk Hossain | (none) | salt-modeling, SALT | Modeling docs hub: dataset-path registry + results leaderboard
SALT / SaaS product | CORE-1533 | Todo | No priority | SALT: Metrics & Scoring Engine | Alok Parlikar | (none) | salt-modeling, SALT | Determine Model Acceptance Criteria (with Karen & team)
SALT / SaaS product | CORE-1534 | Todo | No priority | SALT: Metrics & Scoring Engine | Jeff Lilly | (none) | salt-modeling, SALT | Dashboard: convention-pipeline component F1 / accuracy metrics
SALT / SaaS product | CORE-1535 | In Review | No priority | SALT: Web App Core | Guillermo Segovia | (none) | Feature, SALT | Warn user before applying AI conventions over manual transcript edits (undo risk)
SALT / SaaS product | CORE-219 | Todo | No priority | SALT: Backend Architecture & API | (unassigned) | (none) | SALT | Review DB Schema
SALT / SaaS product | CORE-230 | In Review | No priority | SALT: Backend Architecture & API | Penpicha Sangsanga | (none) | SALT | Verify endpoints use RBAC
SALT / SaaS product | CORE-243 | Todo | No priority | SALT: Backend Architecture & API | (unassigned) | (none) | SALT | Implement Dead Letter Queue (DLQ) for Corrupt Files
SALT / SaaS product | CORE-436 | Todo | No priority | SALT: Transcription Pipeline | (unassigned) | (none) |  | Add other end of utterance punctuation ! > ^ ~ (Priority 8)
SALT / SaaS product | CORE-444 | Todo | No priority | SALT: Backend Architecture & API | Penpicha Sangsanga | (none) |  | Generate and Review API Spec
SALT / SaaS product | CORE-448 | In Progress | No priority | SALT: Metrics & Scoring Engine | arif@cobaltspeech.com | (none) | SALT, salt-modeling | Create test suite for end to end Salt Metrics
SALT / SaaS product | CORE-474 | In QA | No priority | SALT: Web App Core | Jeremy Blair | (none) | SALT | feat(salt): real-time mode flag + per-org quota enforcement
SALT / SaaS product | CORE-486 | In Progress | No priority | SALT: Web App Core | pooja@cobaltspeech.com | (none) | SALT | QA deployed demo: end-to-end walkthrough and bug triage
SALT / SaaS product | CORE-494 | Todo | No priority | SALT: Web App Core | (unassigned) | (none) |  | Add Remotion videos as guides
SALT / SaaS product | CORE-498 | In QA | No priority | SALT: Web App Core | Jeremy Blair | (none) |  | Orgs need a BAA
SALT / SaaS product | CORE-500 | Todo | No priority | SALT: Infrastructure and Deployment | Shahruk Hossain | CORE-626 | SALT | Update model in salt-transcriber deployment
SALT / SaaS product | CORE-501 | Todo | No priority | SALT: Transcription Pipeline | Shahruk Hossain | (none) | SALT | Remove redundant example pipeline configs in saltier
SALT / SaaS product | CORE-502 | Todo | No priority | SALT: Infrastructure and Deployment | Shahruk Hossain | CORE-626 | SALT | Fix SALT pipeline archives on S3
SALT / SaaS product | CORE-576 | Todo | No priority | SALT: Transcription Pipeline | stan@cobaltspeech.com | (none) | SALT, salt-modeling | Validate Parakeet timestamp accuracy
SALT / SaaS product | CORE-577 | Todo | No priority | SALT: Transcription Pipeline | stan@cobaltspeech.com | (none) | Feature, SALT, salt-modeling | Re-calibrate unintelligible segment detector using Parakeet confidence scores
SALT / SaaS product | CORE-580 | In Progress | No priority | SALT: Transcription Pipeline | stan@cobaltspeech.com | (none) | SALT, salt-modeling | Remove invalid and empty files from test and dev sets
Other workstream | CORE-1031 | Todo | Urgent | DJ Mix Studio | (unassigned) | (none) |  | Initialize GitHub repository and project directory structure
Other workstream | CORE-1032 | Todo | Urgent | DJ Mix Studio | (unassigned) | (none) |  | Start PostgreSQL via Docker Compose and configure environment
Other workstream | CORE-1033 | Todo | Urgent | DJ Mix Studio | (unassigned) | (none) |  | Install ffmpeg on development machine
Other workstream | CORE-1034 | Todo | Urgent | DJ Mix Studio | (unassigned) | (none) |  | Set up Go module, install dependencies, and run database migrations
Other workstream | CORE-1035 | Todo | Urgent | DJ Mix Studio | (unassigned) | (none) |  | Set up Python virtual environment and install mixer dependencies
Other workstream | CORE-1047 | Todo | Urgent | DJ Mix Studio | (unassigned) | (none) |  | Push all scaffolded code to GitHub repository
Other workstream | CORE-1583 | In Review | Urgent | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke, Bug | Customer #1: "flip the camera" maps to recording command (should be scope_flip)
Other workstream | CORE-1586 | In Review | Urgent | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke, Bug | Customer #4: "Set brightness to high" — command param empty (level_mode vs brightness_mode mismatch)
Other workstream | CORE-1588 | In Review | Urgent | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke, Bug | Customer #6 (CRITICAL): "Set insufflator pressure" maps to insufflator_start ("insufflator on")
Other workstream | CORE-1591 | In Review | Urgent | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke, Bug | Customer #9: "Set flow rate" → "no type or value" (should map to insufflator_flow_set_command)
Other workstream | CORE-549 | In Progress | Urgent | (none) | Jeremy Blair | CORE-547 |  | MVP Sub-issue 2 — Compliance (Production Bar)
Other workstream | CORE-635 | In Review | Urgent | (none) | Jeremy Blair | CORE-626 |  | Production: Domain decision + procurement
Other workstream | CORE-848 | In QA | Urgent | (none) | Jeremy Blair | CORE-549 |  | Rip out non-compliant Gemini REST path in shared/ai/gemini.go (spice not planned)
Other workstream | CORE-899 | In QA | Urgent | (none) | Guillermo Segovia | CORE-549 | SALT | Convention editor: remove OpenAI/OpenRouter LLM paths — Vertex-only (BAA) for SALT transcript AI
Other workstream | CORE-939 | In Progress | Urgent | Agent-Control Landing Page | Jeremy Blair | CORE-970 |  | Wire auth CTA and test login flow
Other workstream | CORE-1036 | Todo | High | DJ Mix Studio | (unassigned) | (none) |  | Verify Go API tracks endpoints work end-to-end
Other workstream | CORE-1037 | Todo | High | DJ Mix Studio | (unassigned) | (none) |  | Verify Go API mixes and mix-tracks endpoints
Other workstream | CORE-1038 | Todo | High | DJ Mix Studio | (unassigned) | (none) |  | Test mix generation pipeline end-to-end (POST /generate → job polling → download)
Other workstream | CORE-1039 | Todo | High | DJ Mix Studio | (unassigned) | (none) |  | Test thumbnail upload, auto-generation, and preview endpoint
Other workstream | CORE-1040 | Todo | High | DJ Mix Studio | (unassigned) | (none) |  | Set up React frontend (npm install + dev server running)
Other workstream | CORE-1041 | Todo | High | DJ Mix Studio | (unassigned) | (none) |  | Test Track Library UI (add YouTube URL, add file upload, status polling, delete)
Other workstream | CORE-1042 | Todo | High | DJ Mix Studio | (unassigned) | (none) |  | Test Mix Builder UI (create mix, add tracks, reorder, generate, progress bar)
Other workstream | CORE-1077 | In Progress | High | (none) | Jeremy Blair | (none) |  | Release: promote the CORE-817 student stack to master via the integration branch
Other workstream | CORE-1196 | In Progress | High | (none) | (unassigned) | (none) |  | Hard Delete (Admin) — session-level and org-level
Other workstream | CORE-1210 | In Review | High | (none) | (unassigned) | CORE-1065 | SALT, Bug | License seat count not updating — reverts to previous value after "Update license count"
Other workstream | CORE-1381 | In QA | High | (none) | Guillermo Segovia | (none) |  | Remove all frontend-direct Gemini/LLM calls from SALT convention editor (backend-only LLM)
Other workstream | CORE-1383 | Todo | High | (none) | Guillermo Segovia | (none) |  | Consent GCS objects bypass speaker right-to-erasure (off session prefix tree)
Other workstream | CORE-1385 | Todo | High | (none) | Guillermo Segovia | (none) |  | Verify infra-layer HIPAA controls for PHI buckets (BAA, encryption, retention, data-access logging)
Other workstream | CORE-1388 | In QA | High | (none) | (unassigned) | (none) |  | saltier-worker: set NUMBA_CACHE_DIR so Parakeet/NeMo loads in the read-only Nix store
Other workstream | CORE-1391 | In Review | High | (none) | Jeremy Blair | (none) |  | AdminUpdateMemberRole self-demotion guard compares Clerk authUserID to a users.uid — guard is dead
Other workstream | CORE-1403 | In Review | High | BERT NLU Toolkit (SoW6 T2) | (unassigned) | (none) | Diatheke, Bug | Build bug: `diathekemodel train chosun` doesn't regenerate regex.yaml (silent 148→118 regression)
Other workstream | CORE-1411 | Todo | High | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke, Feature | Forward ExpectedEntities over the gRPC NLU path
Other workstream | CORE-1431 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Bug | energy_mode_set dialog: prompt for monopolar_bipolar (new IxD energy-mode flow)
Other workstream | CORE-1432 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Bug | Brightness dialog: required-slot prompt on "set", optional slots on inc/dec, no over-prompt for "set brightness to low"
Other workstream | CORE-1435 | In Review | High | (none) | (unassigned) | (none) | SALT | Multi-role org membership — assign multiple org roles per member (Users tab)
Other workstream | CORE-1456 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Bug | Increase/decrease vs set: per-feature intent behavior (Sarthak's spec)
Other workstream | CORE-1468 | In Progress | High | (none) | Jeremy Blair | (none) |  | Admin assign-subscription: org selector submits auth_system_id, 500s on orgs with an external id
Other workstream | CORE-1475 | In Progress | High | (none) | Jeremy Blair | (none) |  | Gate checkout returns: verify before declaring success (no silent success on delayed/failed webhook)
Other workstream | CORE-1514 | In QA | High | (none) | (unassigned) | (none) |  | saltier-worker: torch/torchaudio version mismatch (torchaudio 2.11 needs CUDA 13, torch 2.10 ships CUDA 12) breaks NeMo import
Other workstream | CORE-1538 | In Review | High | BERT NLU Toolkit (SoW6 T2) | david@cobaltspeech.com | (none) | Diatheke, Bug | BERT training diverges (loss ~1e33, inf grad) in chosun #torchTrain nix env
Other workstream | CORE-1539 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Bug | diathekesvr panics (index out of range) on NaN intent confidences in getCandidates
Other workstream | CORE-1547 | In Review | High | (none) | Jeremy Blair | (none) |  | Checkout fails in all deployed envs: invalid success_url (CORS_ALLOWED_ORIGINS unset → redirect guard fails closed)
Other workstream | CORE-1577 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Feature | SoW T4.3: IxD flowcharts → TSVs → permutation testsets for energy & insufflation dialogs
Other workstream | CORE-1584 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke, Bug | Customer #2: brightness incr/decr over-prompts for a level ("Set brightness to what level?")
Other workstream | CORE-1587 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke | Customer #5: remove final replies from brightness/force-feedback-set/energy-wattage/scope-flip/insufflation/timer/smoke-evac commands
Other workstream | CORE-1589 | In Review | High | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke, Bug | Customer #7: "Set insufflator mode" fires mode command before prompting; prompt arrives after command result
Other workstream | CORE-1593 | In QA | High | (none) | Jeremy Blair | (none) |  | Self-serve transcription blocked by unconditional speaker-consent gate at finalize
Other workstream | CORE-547 | In Progress | High | (none) | Jeremy Blair | CORE-262 |  | MVP Release Checklist — Salt SaaS
Other workstream | CORE-548 | In QA | High | (none) | (unassigned) | CORE-547 |  | MVP Sub-issue 1 — Security & Operational Readiness
Other workstream | CORE-550 | In Progress | High | (none) | Jeremy Blair | CORE-547 |  | MVP Sub-issue 3 — Core Feature Completeness (Salt LSA)
Other workstream | CORE-553 | Todo | High | (none) | Jeremy Blair | CORE-547 |  | MVP Sub-issue 6 — Environments (Staging & Production)
Other workstream | CORE-554 | In Progress | High | (none) | Jeremy Blair | CORE-624 |  | MVP Sub-issue 7 — Branching & Deployment Strategy
Other workstream | CORE-555 | Todo | High | (none) | Jeremy Blair | CORE-547 |  | MVP Sub-issue 8 — Move Salt SaaS off AWS
Other workstream | CORE-561 | Todo | High | (none) | Jeremy Blair | CORE-549 |  | Update Terms of Service and Privacy Policy for Salt SaaS MVP
Other workstream | CORE-650 | In QA | High | Stripe Integration for Billing and Subscriptions | (unassigned) | (none) | SALT, Bug | Don't persist incomplete Stripe subscriptions to org_subscriptions
Other workstream | CORE-674 | In QA | High | (none) | Guillermo Segovia | (none) |  | Revert Analysis tab to generic score layout from SALT analysis/scores page
Other workstream | CORE-706 | In Progress | High | AgroVerify Edge — Design & Development | (unassigned) | (none) |  | [Phase 3] Background Sync & ERP Integration
Other workstream | CORE-822 | In Review | High | (none) | (unassigned) | (none) |  | Admin gate broken: GetMyPermissions dev fallback grants admin to any unresolved caller
Other workstream | CORE-826 | In Review | High | (none) | (unassigned) | (none) |  | Self-serve org creation grants the global Admin role at org scope (org owners become platform admins)
Other workstream | CORE-827 | In QA | High | (none) | Jeremy Blair | (none) |  | identity.users allows duplicate emails — no unique constraint; cross-Clerk-instance login forks a second identity
Other workstream | CORE-851 | In QA | High | (none) | Guillermo Segovia | (none) |  | New Session: skip product-selection step until Spice is integrated
Other workstream | CORE-856 | In QA | High | (none) | Guillermo Segovia | (none) |  | Transcriber portal: manager override to unclaim/reassign sessions (keep edits)
Other workstream | CORE-1004 | In QA | Medium | (none) | Guillermo Segovia | (none) | SALT | Migrate session-read view-all gate from org-admin role to a view-all-org-sessions RBAC permission
Other workstream | CORE-1006 | In QA | Medium | (none) | (unassigned) | (none) |  | Add refs/tags/v* to cicd-builder WIF binding before enabling prod tag deploys
Other workstream | CORE-1043 | Todo | Medium | DJ Mix Studio | (unassigned) | (none) |  | Test thumbnail upload UI and preview in Mix Builder
Other workstream | CORE-1044 | Todo | Medium | DJ Mix Studio | (unassigned) | (none) |  | Cross-browser testing (Chrome, Firefox, Safari, Edge)
Other workstream | CORE-1045 | Todo | Medium | DJ Mix Studio | (unassigned) | (none) |  | Test MP4 export and verify YouTube upload compatibility
Other workstream | CORE-1046 | Todo | Medium | DJ Mix Studio | (unassigned) | (none) |  | Create and publish first proof-of-concept YouTube mix
Other workstream | CORE-1050 | Todo | Medium | (none) | david@cobaltspeech.com | (none) |  | Saltier worker SALT-coding accuracy: gold eval findings + prioritized fixes
Other workstream | CORE-1054 | In QA | Medium | (none) | Jeremy Blair | (none) |  | Control plane: surface (don't swallow) instance billing query errors — blank subscriptions view during deploy skew
Other workstream | CORE-1141 | In Review | Medium | (none) | (unassigned) | (none) |  | Stripe client: remove process-global stripe.Key mutex (per-request API key)
Other workstream | CORE-1147 | In QA | Medium | (none) | Guillermo Segovia | (none) | SALT | Hide gender field on speaker intake forms behind a feature flag (keep plumbing)
Other workstream | CORE-1155 | In QA | Medium | (none) | Guillermo Segovia | CORE-550 | SALT | Raise audio upload cap from 100 MB to 200 MB (LSA new-session upload)
Other workstream | CORE-1156 | In QA | Medium | (none) | Guillermo Segovia | CORE-550 | SALT, Bug | Convention editor (/transcribe) is not responsive — breaks on mobile / narrow viewports
Other workstream | CORE-1157 | In QA | Medium | (none) | Guillermo Segovia | CORE-550 | SALT | Convention editor: remove the "Demo" mode toggle before GTM
Other workstream | CORE-1163 | Todo | Medium | (none) | Guillermo Segovia | CORE-550 | SALT | Verify site demo mode + product tour work correctly with the transcription editor
Other workstream | CORE-1209 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Validate Clerk key pair at startup; redirect signed-in users from auth pages
Other workstream | CORE-1239 | Todo | Medium | (none) | Guillermo Segovia | (none) |  | Convention editor: header hide plugin — hidden caret / hard_break / selection edge cases
Other workstream | CORE-1281 | Todo | Medium | (none) | Jeremy Blair | (none) |  | Transfer mechanism: Move records between organizations
Other workstream | CORE-1307 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Precompute audio waveform peaks to fix slow/janky convention-editor player
Other workstream | CORE-1384 | Todo | Medium | (none) | Guillermo Segovia | (none) |  | Audio signed-URL (15min TTL) expires mid-stream on long recordings → player stalls
Other workstream | CORE-1392 | In QA | Medium | (none) | (unassigned) | (none) |  | saltier-worker: conventions mode drops pause markers (transcribe -> apply conventions)
Other workstream | CORE-1397 | In Review | Medium | Reply ID to Client (SoW6 T3) | (unassigned) | (none) | Diatheke, Bug | Client reply_id integration: py-genproto pin silently no-ops on reinstall
Other workstream | CORE-1415 | In Review | Medium | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Feature | Fill ParseResponse (BERT result + confidences) in the Command Action (SoW T4.5)
Other workstream | CORE-1433 | In Review | Medium | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Bug | media_resize needs a required size slot with a prompt
Other workstream | CORE-1436 | In Review | Medium | (none) | Jeremy Blair | (none) |  | Signed audio-upload URL ignores UploadURLTTL config (hardcoded 15m) → intermittent 403 "Request has expired"
Other workstream | CORE-1437 | In Review | Medium | Reply ID to Client (SoW6 T3) | david@cobaltspeech.com | (none) | Diatheke, Feature | Split prompt vs reply YAML files (reply_id follow-up)
Other workstream | CORE-1443 | In QA | Medium | (none) | (unassigned) | (none) |  | CI fmt-check: prettier EACCES on read-only node_modules cache dir
Other workstream | CORE-1452 | In Progress | Medium | (none) | (unassigned) | (none) | salt-modeling, Experiment | [SALT] C-unit segmenter — neural (shipped) + acoustic-timing extension
Other workstream | CORE-1454 | In Review | Medium | (none) | (unassigned) | (none) |  | [SALT] Pipeline perf — share one spaCy instance across converters
Other workstream | CORE-1459 | Todo | Medium | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Bug | Wire slot-fill extractor into the built chosun model — slot-fill is inert in deployed models until then
Other workstream | CORE-1464 | In Review | Medium | (none) | (unassigned) | (none) |  | Collapse Individual/Enterprise into a single "Standard" plan; make org_type & billing_mode independent of plan
Other workstream | CORE-1466 | In QA | Medium | (none) | Guillermo Segovia | (none) | SALT, Bug | Prof-services reviewers 403 on convention-editor AI passes (/conventions, /retranscribe) — same seat gate as CORE-1442
Other workstream | CORE-1467 | In Progress | Medium | (none) | Jeremy Blair | (none) |  | Admin org settings: consolidated subscription card + per-org feature grants
Other workstream | CORE-1469 | In Progress | Medium | (none) | Jeremy Blair | (none) |  | Admin assign-subscription: surface a clear error instead of a silent failure / raw 500
Other workstream | CORE-1470 | In Progress | Medium | (none) | Jeremy Blair | (none) |  | run-stack.sh: enable Stripe CLI webhook forwarding for local dev so paid checkouts sync
Other workstream | CORE-1472 | In Progress | Medium | (none) | Jeremy Blair | (none) |  | Org admin can rename the org from the org-settings (Plan & Licenses) page
Other workstream | CORE-1473 | In Progress | Medium | (none) | Jeremy Blair | (none) |  | Admin account-class flip: replace native window.prompt/alert with an inline confirm + reason
Other workstream | CORE-1474 | In Progress | Medium | (none) | Jeremy Blair | (none) |  | Demo tour tooltip renders off-screen near viewport edges; clamp it into view
Other workstream | CORE-1540 | In Progress | Medium | BERT NLU Toolkit (SoW6 T2) | david@cobaltspeech.com | (none) | Diatheke | chosun nix flake torchTrain devshell: pinned-old nixpkgs, hand-built deepspeed/torchvision, GPU needs nixglhost
Other workstream | CORE-1544 | In QA | Medium | (none) | Jeremy Blair | CORE-850 |  | Automated bypass-mode E2E for signup/registration funnels (Clerk server-boundary fake)
Other workstream | CORE-1567 | In Review | Medium | Wakeword Model & Monitoring (SoW6 T1) | Penpicha Sangsanga | (none) | Diatheke, Feature | Internal wakeword API: robustly parse both single and comma-separated WakeWord
Other workstream | CORE-1576 | In Review | Medium | Diatheke Usability & Slot Filling (SoW6 T4) | david@cobaltspeech.com | (none) | Diatheke, Bug | brightness_level_set: command inputs + brightness_mode/level_mode overlap
Other workstream | CORE-1579 | In Progress | Medium | NLU Eval Harness (Diatheke / Chosun) | (unassigned) | (none) | Diatheke | Add false-positive (adversarial) NLU test to the standard model-release test suite
Other workstream | CORE-1580 | In QA | Medium | (none) | (unassigned) | (none) |  | Devcontainer: natively-run frontends can't reach backends (run-stack network wiring)
Other workstream | CORE-1581 | In Review | Medium | NLU Eval Harness (Diatheke / Chosun) | (unassigned) | (none) | Diatheke | Task-completion scorer: capture reply_id from ReplyAction (now sent over the API)
Other workstream | CORE-1590 | In Review | Medium | Diatheke Usability & Slot Filling (SoW6 T4) | (unassigned) | (none) | Diatheke | Customer #8: support "insufflator preset" verbiage for insufflator mode
Other workstream | CORE-1596 | In Review | Medium | (none) | Shahruk Hossain | (none) | salt-modeling, SALT | Saltier worker: enforce configurable max audio duration + file size
Other workstream | CORE-1633 | In Review | Medium | (none) | Shahruk Hossain | (none) | SALT | Frontend: pre-upload audio size + duration check with user alert
Other workstream | CORE-1634 | In Review | Medium | (none) | Shahruk Hossain | (none) | SALT | Convention editor: enforce 6000-word transcript limit (gate + alert)
Other workstream | CORE-464 | Todo | Medium | (none) | Jeremy Blair | (none) | SALT, Feature | Break out DDL and goose rights from API IAM
Other workstream | CORE-562 | In Review | Medium | (none) | Alok Parlikar | CORE-549 |  | E-signature vendor decision: clickwrap (Funnel A), sales-led (Funnel B), Zoho Sign (Funnel C)
Other workstream | CORE-667 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Remove Transcriber Queue and Reviewer Queue sidebar links — queues belong on the Transcriber dashboard
Other workstream | CORE-807 | In QA | Medium | (none) | (unassigned) | (none) |  | /settings/team has no sidebar nav entry — reachable only by direct URL
Other workstream | CORE-816 | In Review | Medium | (none) | Jeremy Blair | CORE-550 |  | SALT student subscription + seat & invite model + per-session cost tracking
Other workstream | CORE-817 | In QA | Medium | (none) | Jeremy Blair | CORE-816 |  | 3-year student subscription ($80 / 3 years) during registration
Other workstream | CORE-819 | In Review | Medium | (none) | Jeremy Blair | CORE-816 |  | Admin can self-assign / unassign a seat
Other workstream | CORE-824 | In Review | Medium | (none) | (unassigned) | (none) |  | No startup guard against frontend/backend Clerk instance mismatch
Other workstream | CORE-852 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Clinician dashboard: three session statuses + transcript source column
Other workstream | CORE-855 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Clinician notes section on submission to transcription services
Other workstream | CORE-857 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Transcribe dashboard: assigned transcriber/reviewer name not showing
Other workstream | CORE-859 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Submit for review: optional assignment to a specific reviewer
Other workstream | CORE-860 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Configurable review stages: AI first pass + peer review
Other workstream | CORE-867 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Convention editor: improve analysis/editor load time
Other workstream | CORE-870 | In QA | Medium | (none) | Guillermo Segovia | (none) |  | Convention editor: hide Phase 1 (transcription) from clinicians, auto-populate headers
Other workstream | CORE-887 | Todo | Medium | (none) | Jeremy Blair | (none) |  | Extend email canonicalization to org_invites (case-insensitive parity) + cleanup
Other workstream | CORE-928 | In QA | Medium | (none) | Guillermo Segovia | (none) | SALT | Convention editor — dark-mode pass (brand tokens → CSS custom properties + ~200-class dark: sweep)
Other workstream | CORE-930 | In QA | Medium | (none) | Guillermo Segovia | (none) | SALT | Wire convention-editor Playwright e2e specs into CI
Other workstream | CORE-933 | In QA | Medium | (none) | Guillermo Segovia | (none) | SALT | Upload-transcript jobs create no session row — invisible on session dashboards/queue
Other workstream | CORE-1056 | In QA | Low | (none) | Jeremy Blair | (none) |  | docs/SAAS_REQUIREMENTS.md: resolve duplicate requirement IDs G-BILL-20/21/22/23
Other workstream | CORE-1057 | In QA | Low | (none) | Jeremy Blair | (none) |  | Fix stale intro-copy assertion in subscription.spec.ts (doesn't match rendered text)
Other workstream | CORE-1404 | In Review | Low | BERT NLU Toolkit (SoW6 T2) | (unassigned) | (none) | Diatheke | transformers version drift: training smoke-test on pinned nix versions
Other workstream | CORE-1458 | In Review | Low | (none) | Alok Parlikar | (none) |  | Auto-refresh nix vendorHash/npmDepsHash on Dependabot PRs
Other workstream | CORE-1465 | In Review | Low | (none) | (unassigned) | (none) |  | e2e: run Playwright dev server with Turbopack to eliminate cold-compile false failures
Other workstream | CORE-1471 | In Progress | Low | (none) | Jeremy Blair | (none) |  | Show the Student plan card in the inline Plan & Licenses settings tab
Other workstream | CORE-1630 | In Review | Low | (none) | Shahruk Hossain | (none) | salt-modeling, SALT | Saltier worker: reject oversized audio before GCS download (blob.size metadata)
Other workstream | CORE-556 | Todo | Low | (none) | Jeremy Blair | CORE-547 |  | MVP Sub-issue 9 — Post-MVP backlog (parent for deferred work)
Other workstream | CORE-675 | In QA | Low | (none) | Jeremy Blair | (none) |  | Frontend: add Next.js ESLint config and fix all lint violations
Other workstream | CORE-808 | In Review | Low | (none) | (unassigned) | (none) |  | Duplicate "Team" nav entry in components/salt/sidebar.tsx (key collision)
Other workstream | CORE-1059 | In Review | No priority | (none) | (unassigned) | (none) |  | [frontend] feat(speakers): gender field, future-DOB guard, card-grid picker (PR #331)
Other workstream | CORE-1060 | In QA | No priority | (none) | (unassigned) | (none) |  | First-run setup wizard for fresh instance bootstrap (site-admin)
Other workstream | CORE-1144 | Todo | No priority | (none) | Jeremy Blair | CORE-550 |  | Decision record: speaker metadata by product (SALT vs SPICE)
Other workstream | CORE-1158 | In QA | No priority | (none) | Guillermo Segovia | (none) |  | SALT transcription editor — SALTRoadmap alignment (report + proceed-to-report flow)
Other workstream | CORE-1160 | In QA | No priority | (none) | Guillermo Segovia | CORE-1158 |  | Re-surface database selection after Proceed to Report
Other workstream | CORE-1161 | In QA | No priority | (none) | Guillermo Segovia | CORE-1158 |  | Transcript-responsibility acknowledgment modal after Proceed to Report
Other workstream | CORE-1162 | In QA | No priority | (none) | Guillermo Segovia | CORE-1158 |  | Editor layout: steps left, shortcuts right, SALT header behind View SALT Header
Other workstream | CORE-1198 | In Review | No priority | (none) | (unassigned) | CORE-1196 |  | Hard Delete: session-level implementation
Other workstream | CORE-1199 | In Review | No priority | (none) | (unassigned) | CORE-1196 |  | Hard Delete: org-level implementation
Other workstream | CORE-1211 | In Progress | No priority | (none) | Jeremy Blair | CORE-1196 |  | [TPM] Hard Delete: org-level consent-doc GCS purge + compliance (T3b)
Other workstream | CORE-1284 | In Review | No priority | (none) | Jeff Lilly | (none) |  | Punctuation-agnostic C-unit & maze boundary scoring in eval/conventions
Other workstream | CORE-1393 | In QA | No priority | Wakeword Model & Monitoring (SoW6 T1) | Penpicha Sangsanga | (none) | Diatheke, Feature | Wakeword monitoring: config thresholds + WakewordResult location/accepted
Other workstream | CORE-1398 | In Review | No priority | BERT NLU Toolkit (SoW6 T2) | david@cobaltspeech.com | (none) | Diatheke, Feature | Embed chosun_torch for inline BERT training (embed_torch build tag)
Other workstream | CORE-1399 | In Review | No priority | BERT NLU Toolkit (SoW6 T2) | david@cobaltspeech.com | (none) | Diatheke, Bug | BERT training robustness for diathekemodel pipelines
Other workstream | CORE-1400 | In Review | No priority | BERT NLU Toolkit (SoW6 T2) | david@cobaltspeech.com | (none) | Diatheke, Feature | Slim BERT training import closure (lazy deepspeed/hyperopt/higher)
Other workstream | CORE-1401 | In Review | No priority | BERT NLU Toolkit (SoW6 T2) | david@cobaltspeech.com | (none) | Diatheke, Bug | pynvml unconditional import breaks packaged train.py env
Other workstream | CORE-1417 | Todo | No priority | NLU Eval Harness (Diatheke / Chosun) | david@cobaltspeech.com | (none) | Diatheke, Feature | Entity-level eval harness (chosun cmd/entityeval)
Other workstream | CORE-1476 | In Review | No priority | (none) | Jeremy Blair | (none) |  | License-change UX: proration preview + confirmation in Change-My-Plan modal
Other workstream | CORE-1477 | In Review | No priority | (none) | Jeremy Blair | (none) |  | Invoiced orgs: license changes via Stripe invoice items + invoice mirror/webhook sync
Other workstream | CORE-1478 | In Review | No priority | (none) | Jeremy Blair | (none) |  | Admin "Invoices" tab — list invoices (status/detail) + PDF download
Other workstream | CORE-1552 | In QA | No priority | (none) | Guillermo Segovia | (none) |  | SALT new-session: CA confirmation line hidden for infants (0;N months)
Other workstream | CORE-1553 | In QA | No priority | (none) | Guillermo Segovia | (none) |  | SALT new-session: ?speaker= deep-link shows empty picker + green step on fetch failure
Other workstream | CORE-1592 | In Review | No priority | (none) | Shahruk Hossain | (none) | salt-modeling, SALT | SALT scores agreement report + saltier-diff correctness fixes
Other workstream | CORE-33 | Todo | No priority | CAPT Model v2026.01 Airworthiness | Shahruk Hossain | (none) |  | Prepare REAL testset to evaluate CAPT performance
Other workstream | CORE-435 | Todo | No priority | (none) | (unassigned) | (none) | SALT | Transcription Does Not Handle Network Interruption Gracefully
Other workstream | CORE-443 | Todo | No priority | (none) | Shahruk Hossain | (none) |  | [Vanta] Remediate "Critical vulnerabilities identified in packages are addressed (GitHub Repo)"
Other workstream | CORE-495 | In Review | No priority | Support - Verint Redaction | Guillermo Segovia | (none) |  | Verint Hebrew Redaction
Other workstream | CORE-569 | In Progress | No priority | (none) | Jeff Lilly | (none) |  | Create IPSyn scoring report from CLAN code
Other workstream | CORE-570 | Todo | No priority | (none) | Jeff Lilly | (none) |  | Create LLM help bot for SALT
Other workstream | CORE-594 | In QA | No priority | (none) | Guillermo Segovia | CORE-829 |  | Expand contraction & possessive marking coverage
Other workstream | CORE-596 | In QA | No priority | (none) | Guillermo Segovia | CORE-829 |  | Preserve edits & conventions across transcript edits
Other workstream | CORE-597 | In QA | No priority | (none) | Guillermo Segovia | CORE-832 |  | Export analysis for customers who don't have SALT
Other workstream | CORE-598 | In Progress | No priority | (none) | Guillermo Segovia | CORE-830 |  | Surface elapsed time + word/utterance counts; 50-utterance stop heuristic for Play/Con/SSS
Other workstream | CORE-599 | In QA | No priority | (none) | Guillermo Segovia | CORE-829 |  | SI code per utterance — edit-menu parity with SALT
Other workstream | CORE-925 | In Review | No priority | WO-2026-06-06-spice-rack-footer | Jeremy Blair | CORE-968 |  | Create Footer component with dynamic copyright
Other workstream | CORE-926 | In Review | No priority | WO-2026-06-06-spice-rack-footer | Jeremy Blair | CORE-968 |  | Integrate Footer into root layout
Other workstream | CORE-927 | In Review | No priority | WO-2026-06-06-spice-rack-footer | Jeremy Blair | CORE-968 |  | Verify footer responsive behavior
Other workstream | CORE-968 | In Review | No priority | WO-2026-06-06-spice-rack-footer | Jeremy Blair | (none) |  | Add footer with copyright to Cobalt application
Other workstream | CORE-972 | In Progress | No priority | WO-2026-06-06-playwright-testing | Jeremy Blair | (none) |  | Comprehensive Test Coverage for Spice Rack
Other workstream | CORE-973 | In QA | No priority | WO-2026-06-06-playwright-testing | Jeremy Blair | CORE-972 |  | [QA] Phase 1: Mobile E2E Tests
Other workstream | CORE-974 | In QA | No priority | WO-2026-06-06-playwright-testing | Jeremy Blair | CORE-972 |  | [QA] Phase 2: Funnel Edge Case Tests
Other workstream | CORE-976 | In Review | No priority | WO-2026-06-06-playwright-testing | Jeremy Blair | CORE-972 |  | [Fullstack] Phase 4: Component Tests

## Legend
Legend
Snapshot: verified against git 2026-07-01 ¦ Generated 2026-07-03
Key | Definition
Major release | A release that does NOT roll up into another release (e.g. Mars, Orion, Rust, Transcriber Portal 1.1).
Minor / sub-release | A release that rolls up into a parent major release (e.g. Mercury/Saturn/Lyra/Pluto/Earth roll up into Mars; Neptune/Bull roll up into Orion). Shown as ' ↳ <name>' under its major.
Codename | The release's short project codename as used in branch names and Linear titles.
Linear | The Linear issue ID for this release/feature, hyperlinked to the ticket.
Status (effective) | Computed status: if the item is on master (master = ☑) it is 'Done'. Otherwise this shows its current Linear status.
Linear status | The status the ticket actually reports right now in Linear (as of the snapshot date).
⚠ Stale? | Flag: '⚠ update Linear → Done' when the item is on master (effectively Done) but its Linear status is still non-terminal (not Done/Canceled). This flags tickets a human should flip to Done in Linear. The agent that built this sheet never changes Linear itself — Done is a human decision, this is only a flag.
Integration branch | The named git branch that gathers this release's/sub-release's constituent PRs before promotion (e.g. jeremy/integration-mars).
dev / staging / master(=prod) | Environment checkboxes. ☑ = the integration branch is merged into that environment's long-lived branch (dev / staging / master). ☐ = not merged. Per team convention, master = prod branch (NOT a deployed prod release — see Prod deployed?).
In integration branch? | (Tab 2 only) Whether this specific feature/fix has actually landed in its release's integration branch yet (Yes/No) — distinguishes 'committed to release scope' from 'code has landed'.
Prod deployed? | ☑ only if a vX.Y.Z tag was cut on master AND deploy-prod.yml was run. As of this snapshot this is 'No' for every release — master = prod BRANCH, not a deployed prod release. No prod deploy has been run yet for any release (confirmed via CORE-1189).
Description | What the release/sub-release/feature is, in plain language.
Notes | Traceability notes: PR numbers, merge commits, exclusions, caveats, and routing decisions pulled from the Linear release-bundle descriptions.
Area (Tab 3) | 'SALT / SaaS product' if the issue's Linear project starts with 'SALT' or is one of: QA for GTM, MARS Audit Remediation, HIPAA/FERPA/COPPA Audit Remediation, Security & Identity Hardening, Levi/Ashley Product Management. Otherwise 'Other workstream' (Diatheke, Wakeword, NLU/BERT, DJ Mix Studio, CAPT, etc. — separate product lines, not on the Cobalt release train).
Not in a Release (Tab 3 scope) | Open Core Team items (status In Progress / In Review / In QA / Todo) that are NOT a constituent of any release manifest on Tabs 1/2, and whose parent issue also isn't a release/constituent. Excludes Backlog and Done/Canceled items entirely.
Status color — green | Done.
Status color — amber | In QA / In Review / In Progress / Researching.
Status color — grey | Backlog / Todo / Planned / Pending / Canceled.
Status color — red | Deferred / Blocked.
Major row shading (Tab 1) | Light blue-grey fill marks a major-release row; its minors are listed italic and indented directly beneath it.
Data sources | Linear CORE-1189 ('Releases' umbrella + Releases roll-up table), each child release bundle's own description ('Bundle manifest' / 'Feature manifest' tables), sub-release children (e.g. Bull under Orion), and a full Core Team list_issues sweep (state=started, state=unstarted) diffed against every manifest issue ID collected above.
Read-only guarantee | This spreadsheet is generated by reading Linear only. No Linear ticket is ever modified, and no ticket is ever marked Done by the generation process — the ⚠ Stale? flag is the only signal surfaced for a human to act on.